## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 2024-04-30
Group Number |  | 40
Participant 1 |  | Matteo Habsburg-Lothringen
Participant 2 |  | Theo Wendel
Participant 3 |  | Yann Polini
Participant 4 |  | Benjamin Zelenay
Participant 5 |  | Michael Kovacevic
Mentor |  | Christoph Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Messenger (extended) | 3 | 2 | -1 | x
2 | Dark/Light Mode/ additional CSS | 2 | 2 | 0 | x
3 | Admin Useroverview (html/sql) | 3 | 3 | 0 | x
4 | Admin Userdata Management | 2 | 3 | 1 |  | x
5 | Admin can change User Passwords | 2 | 2 | 0 | x
6 | User can add/edit/remove Pictures | 3 | 2 | -1 | x
|  |  |  | -1 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol