## Tabelle1
Sprint Review Protocol
Sprint No: |  | 4
Date & Time |  | 2024-05-14
Group Number |  | 40
Participant 1 |  | Matteo Habsburg-Lothringen
Participant 2 |  | Theo Wendel
Participant 3 |  | Yann Polini
Participant 4 |  | Benjamin Zelenay
Participant 5 |  | Michael Kovacevic
Mentor |  | Christoph Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | display Profile + Accountdata | 2 | 2 | 0 | x
2 | User Reporting Function | 3 | 3 | 0 | x
3 | User can change Password | 1 | 1 | 0 | x
4 | Reported Users Dashboard | 3 | 3 | 0 | x
5 | Login/Signup Error Messages | 2 | 2 | 0 | x
6 | Persistent Messaging System | 3 | 5 | 2 |  | x
|  |  |  | 2 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol