## Tabelle1
Sprint Review Protocol
Sprint No: |  | 5
Date & Time |  | 2024-05-28
Group Number |  | 40
Participant 1 |  | Matteo Habsburg-Lothringen
Participant 2 |  | Theo Wendel
Participant 3 |  | Yann Polini
Participant 4 |  | Benjamin Zelenay
Participant 5 |  | Michael Kovacevic
Mentor |  | Christoph Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | User Discovery Feature | 10 | 11 | 1 |  | x | pair programming
2 | Matching System Implementation | 8 | 7 | -1 | x |  | pair programming
|  |  |  | 0 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol